HP — Q3 New-Hire Onboarding Sync

Meeting transcript  |  June 26, 2026  |  Attendees: Priya (IT), Marcus (HR), Dana (Facilities), Sam (Procurement)

TRAINING SAMPLE — fictional transcript for the PL-7008 Copilot Studio course. Not a real HP meeting.

Marcus (HR): Thanks everyone. The July new-hire cohort starts the 14th, and last quarter onboarding felt rushed. Let's lock down owners and dates today.

Priya (IT): Biggest risk is laptops — they arrived late last time. I'll pre-stage 20 laptops for the cohort, but I need the order confirmed first. I can have them imaged and ready by July 10.

Sam (Procurement): I'll confirm the laptop order and send Priya the tracking numbers by July 3 so she's not blocked.

Marcus (HR): Our onboarding portal checklist is out of date — it still references the old VPN process. Priya, can you send me the updated VPN setup steps? Once I have those I'll refresh the checklist.

Priya (IT): Yes, I'll send you the updated VPN setup steps by July 5.

Marcus (HR): Great. I'll update the onboarding portal checklist by July 8, after I get the VPN steps from Priya.

Dana (Facilities): Seating and badges weren't ready last time either. I'll assign desks and set up badge access for the whole cohort by July 9.

Marcus (HR): Perfect. I'll also schedule the new-hire welcome session for July 14 and send calendar invites by July 7.

Sam (Procurement): One more — should we order welcome kits? I can look into it but it's lower priority.

Marcus (HR): Let's note it but it's optional for now. Thanks all — let's make this the smoothest onboarding yet.